## Sheet1
eCOMMERCE BACKLOG
No | As a… | I want to be able to | So that…. | Estimation | Sprint | Status
1 | Administrator | create account | I can use the system | 9 | 1 | not started
2 | Administrator | create users | they can use the system | 5 | 1 | not started
3 | Administrator | create roles | assign them to users | 4 | 1 | not started
4 | Administrator | list roles | I know or remember them | 3 | 1 | not started
5 | Administrator | remove roles | users can not have them | 3 | 1 | not started
6 | Administrator | create privileges | I assign them to users | 4 | 1 | not started
7 | Administrator | list privileges | I know or remember them | 3 | 1 | not started
8 | Administrator | list all users | I know or manage them | 3 | 1 | not started
9 | Administrator | add role to any user | they can use that role in the system | 5 | 1 | not started
10 | Administrator | remove any role to a user | if they are not allowed to have them | 5 | 1 | not started
11 | Administrator | Set site currency | system work with different currencies | 5 | 1 | not started
12 | Customer | create account and login | they can view profile and orders | 10 | 2 | not started
13 | Administrator | create products' category | it can be used to manage products | 5 | 2 | not started
14 | Administrator | update products' category | if there is any change. | 4 | 2 | not started
15 | Administrator | create new product | it can be visible to customers | 5 | 2 | not started
16 | Administrator | update product | if there is any change. | 4 | 2 | not started
17 | Administrator | list products | to know them and manage them | 4 | 2 | not started
18 | Administrator | list categories | to know them and manage them | 4 | 2 | not started
19 | Administrator | disable category | not be visible to customers | 5 | 2 | not started
20 | Customer | create customer profile | customers are described by it | 7 | 2 | not started
21 | Administrator | search customer by name or email | they are known and managed | 7 | 3 | not started
22 | Administrator | view customer profile | to know them and manage them | 5 | 3 | not started
23 | Customer | view categories | they choose products in the category | 4 | 3 | not started
24 | Customer | view products | making order be easy | 3 | 3 | not started
25 | Customer | view products in any category | searching a product be easy | 3 | 3 | not started
26 | Customer | search product | they filter the system to their best desire | 5 | 3 | not started
27 | Customer | view product details | user know all details of a product | 3 | 3 | not started
28 | Customer | add a product to cart | they create an order | 6 | 3 | not started
29 | Customer | update orders | they order at their best willing | 5 | 3 | not started
30 | Customer | update carts products | customer remains with products they need | 4 | 3 | not started
31 | Customer | view products in a cart | customer know them and manage that cart | 5 | 3 | not started
eCOMMERCE BACKLOG
No | As a… | I want to be able to | So that…. | Estimation | Sprint | Status
32 | Customer | receive email of order confirmation | customer know confirmation of their order | 5 | 4 | not started
33 | Customer | pay using credit cards | customer pay in the way they are comfortable | 8 | 4 | not started
34 | Customer | view order history | customer know the orders they made | 6 | 4 | not started
35 | Customer | outstanding orders | customer know their outstanding orders | 6 | 4 | not started
36 | Customer | view order history | customer know them | 4 | 4 | not started
37 | Customer | cancel orders and receive email | the system counts no more that order | 4 | 4 | not started
38 | Administrator | view customer order history | to know them and manage them | 4 | 4 | not started
The project is in 4 Sprints. Each sprint is about 5 days, 20 days to finish this work
The estimation is based on hours.